## Scrum Impact Measures
Process Area Group | Process Area | Activities | Outcome | Best Practices | Stakeholders | Measure | Primary Impact - Quality, Schedule, Cost | Value Delivered (Med/High) | Implementation Timeline - 30/60/90
Process | Backlog Creation & Story Grooming Meeting | 1) Functional & Non functional requirements are defined 2) Groomed stories are discussed with all the stakeholders 3) Have enough features and stories lined up in the backlog for the team to be able to take up more stories to fill team’s capacity at will | 1) Well defined backlog containing features & stories 2) Story Detailing & Discussion 3) Acceptance criterions discussion 4) Story estimation | 1) Story Grooming meeting should happen before the start of the sprint 2) High Level Estimation should happen in the Story grooming meting only so as in sprint planning only gaps are discussed along with committing the stories based on capacity/velocity 3) Definition of Ready should be defined & documented in confluence/SharePoint, each groomed story should satisfy the below parameters: a) Title b) Description c) Should be small enough that can be fit in one sprint d) Concise acceptance criteria(s) should be listed e) List the dependencies should be listed (if any) f) How to demo it and whom to demo, g) Estimation in Story points 4) Team should spend at least 10% of their Sprint length for backlog grooming. For instance, a team that is following 2 week sprint (10 ideal days), the time to be spend should be around 1 day (which is 5 to 6 ideal hours). 5) Atleast 3 Sprints work of the User Stories should be available in the backlog before the start of each sprint | Product Owner Scrum Master QA Dev BA | Productivity Team Improvement Rate Release Burn down | Schedule | High | 60
| Estimation & Capacity Planning | 1) Estimating the story using any of the below techniques: a) Planning poker b) Wideband Delphi Approach c) T-Shirt Sizing 2) Capacity of the team should be identified considering the holidays & leave plans before the sprint planning meeting | 1) Story points for each story 2) Defined capacity & velocity baselined | 1)To improve estimation base stories needs to be identified by both Dev & QA, against which estimation can be carried out. | Product Owner Scrum Master QA Dev BA | Team Capacity Team Velocity | Schedule & Cost | Medium | 60
| Sprint Planning | 1) Team members choose what they would like to work in each sprints 2) Stories gaps are discussed 3) Dev & QA decides how many groomed stories can be completed in the sprint 4) Plan the task in such a way that task load is balanced between all the scrum team members 5) Capacity & baselined velocity are reviewed 6) Plan enough Story points to meet the teams potential velocity | 1) Stories are pulled from Product backlog to Sprint backlog 2) Sprint objectives are defined 3) Capacity & baselined velocity are reviewed to check under or over allocation | 1) Whole team should participate in the Sprint planning meeting. 2) On an average 2 hour is spent on Sprint planning for 2 weeks of Sprint. 3) Buffer of at least 20% should be kept from the capacity for unplanned activities like defects & technical debt reduction along with to manage uncertainties and adhoc tasks 4) Test Data requirements should be captured & respective tasks should be created 5) Once tasks are created, scrum master should check that no team member is under or over allocated & capacity should match with the task loaded hrs. 6) Dev & QA team should collaborate & decide which stories they want to focus on first & rough delivery order of stories should be created so that dev. can get the test plan/test cases for the stories before the unit/integration testing & qa can plan execution activities accordingly. | Product Owner Scrum Master QA Dev BA | Team Capacity Team Velocity Team Allocation Report | Quality | Medium | 30
| Sprint Execution | 1) Daily tasks are discussed with each and every team member 2) Impediments or blocks are raised in daily scrum call 3) Code Review & Unit Testing is carried out by Dev Team for each story & is deployed to QA 4) QA completes the execution & marked the story as Test Complete | 1) Standups are held on daily basis to track team progress 2) Unit testing results are shared with QA 3) Test Cases are shared by QA to Dev team 4) Stories status moves from Ready to Dev Complete to Test Complete | 1) Each team member should talk about following items during scrum & should stick to the below agenda: a) What task was planned for yesterday and if you are able to complete the task as planned – 45 sec (Approx.) b) What is the task that you are planning to perform today – 45 seconds (Approx.) c) Any impediments or blocking issues that needs to be discussed – 45 sec (Approx.) d) Provide clear description of the User Story and tasks worked or planning to work next e) Block the tasks if there is any impediment before the stand-up meeting. 2) Build process should be automated 3) Smoke suite should be automated & integrated with any build tool to achieve CI 4) Using Dev-Dev & Dev-QA pair programming, & incorporating collective code ownership, product quality can be improved 5) Test cases should be classified as High, medium & Low so as risk based testing is achievable when ever required 6) Test cases created by QA should be reviewed by dev. team diligently & review comments provided by dev. team should be incorporated by QA 7) Status of all the acceptance criterions of story after test execution completion should be changed to “Pass” or “Fail” & if it’s marked failed, corresponding bug should be logged in defect management tool 8) Developers should take responsibility of fixing the defects related to the User story assigned to them 9) Status of the story should be changed to “Test Complete” if all the acceptance criterions have been tested by QA & no high priority/severity defect is in open state for the respective story. | Scrum Master QA Dev | NA | Schedule, Cost & Time | High | 90
| Sprint Review | 1) Dev+QA team demonstrates the completed stories to all the stakeholders 2) Product Owner along with business team verifies the story against the "definition of done" | 1) Accepted list of stories where story status is moved from Test Completed to Accepted 2) Stories not meeting the definition of done are splitted & moved to next sprint 3) Any items missed in stories are captured & published in confluence/SharePoint | 1) On an average 3 to 4 hour is spent on Sprint planning for 2 weeks of Sprint. 2) Definition of Done should be defined which should contain below parameters: a) Code should be peer-reviewed b) Story should be unit tested by developer c) All the dev. & QA tasks with respect to story should be complete & no tasks should be blocked or incomplete d) Story is tested against all the acceptance criterions e) All the acceptance criterions should be marked as Pass & there should not be any acceptance criterion which has not been tested or failed f) No defect should be in open/active state g) story is in test complete status h) Product owner accepts the story 3) New stories should be created from items which are missed in any story & should be put in backlog 4) Code refactoring, keeping design simple, defect prioritization & sonar cube implementation keeps check on technical debt 5) Don't let velocity go down from the previous sprint for any reason | Business Owners Product Owner Scrum Master QA Dev BA | Team Velocity Confidence delivery Release velocity Acceleration | Quality | High | 30
| Sprint Retro | In this meeting all team members reflect on the past sprint and check three things: a) What went well during the sprint b) What didn't went well c) What improvements could be made in the next sprint. | 1) Metrics & KPI's prepared before the sprint retro are discussed 2) Action Plan is created based on the team discussion & assigned to respective team members | 1) Before Sprint retro meeting, regression package should be updated to include the current sprint stories high & medium priority test scenarios. 2) Before Sprint retro meeting, Metrics & KPI's should be captured for the sprint & shared with all the stakeholders: 3) Following KPI's should be captured & reported for each sprint a) Team Velocity b) Release velocity Acceleration c) Average Iteration Defect d) Average Productivity e) Team Improvement Rate f) Confidence delivery Below metrics should be captured a) Basic QA Metrics b) Defect Finding Rate c) Test Case Efficiency d) Bad Fix Ratio e) % Test Case Execution f) Trend Analysis g) Sprint Burn down Chart 4) Commit to improve what was discussed in the Sprint retrospective. 5) Measure progress every Sprint Retrospective. 6) No new improvements will be taken until the agreed improvement items are completely addressed. | Product Owner Scrum Master QA Dev BA | 1) Team Velocity 2) Release velocity Acceleration 3) Average Iteration Defect 4) Average Productivity 5) Team Improvement Rate 6) Confidence delivery 7) Basic QA Metrics 8) Defect Finding Rate 9) Test Case Efficiency 10) Bad Fix Ratio 11) % Test Case Execution 12) Trend Analysis 13) Sprint Burn down Chart | Quality | High | 30
Test Tools and Automation | Automation | Told to be used for automation (Smoke & Regression) should be identified during start of first sprint | Automation Tool & Framework will be finalized during first sprint Metrics for capturing the automation status should also be identified | 1) Test Automation & Framework standardization should happen during start of the project & focus should be give to open source tools like Selenium, Soap UI 2) Jenkins/Octopus can be used for implementing CI & automated scripts can be integrated with them. 3) Automation Framework should incorporate the following best practices: a)Tool for managing the build updates like Maven can be used b) Page Object Model to reduce the maintenance efforts c) Test NG Plugin to do priority testing d) Extent/allure reports to get the execution dashboard e) Using Extent/Allure reporting failure snapshot can also be captured f) Using Test NG execution status report can be mailed to all stakeholders 4) Team should focus on completing 100% regression automation since then only we can look forward to In sprint automation 5) Metrics i.e. %Regression automated, Automation Progress, %Automated Test Coverage should be captured | QA Dev | % Regression Automated %Automated Test Coverage Automated Software Testing ROI | Schedule & Cost | Medium | 90